## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Kickoff and Repository Setup – Initialize GitHub repo, define folder structure, set up virtual environment | MUST HAVE | No Dependency | Kuruba Ashok | 3- Completed
S1 | S1 | US-001 | Workflow Creation and Architecture Design – Design system architecture and data flow diagram for ML pipeline | MUST HAVE | Lucid Chart / Draw.io | Kuruba Ashok | 3- Completed
S2 | S2 | US-001 | Agile Document Preparation – Prepare Product Backlog, Sprint Backlog, Stand-up and Retrospection sheets | MUST HAVE | No Dependency | Kuruba Ashok | 3- Completed
S2 | S2 | US-001 | Financial API Integration – Research and integrate Yahoo Finance / Stooq APIs with curl_cffi fallback for NSE data | MUST HAVE | Yahoo Finance / Stooq API | Kuruba Ashok | 3- Completed
S2 | S2 | US-001 | Data Preprocessing Pipeline – Clean raw market data using Pandas; handle NaN, zero prices, MultiIndex columns | MUST HAVE | Pandas, NumPy | Kuruba Ashok | 3- Completed
S3 | S3 | US-001 | ML Model Development – Train RF, ET, GB, XGBoost, LightGBM; build Stacking Ensemble; save 10 pkl files | MUST HAVE | Scikit-learn, XGBoost, LightGBM | Kuruba Ashok | 3- Completed
S4 | S4 | US-001 | FastAPI Backend Development – Design and build RESTful API endpoints for signals, history and backtest | MUST HAVE | FastAPI, Uvicorn | Kuruba Ashok | 3- Completed
S5 | S5 | US-001 | ML and Backend Integration – Integrate pkl prediction pipeline into FastAPI; validate live signal endpoint | MUST HAVE | FastAPI, Scikit-learn, XGBoost | Kuruba Ashok | 3- Completed
S6 | S6 | US-001 | React Frontend Dashboard – Build interactive React dashboard with signal cards and probability bars | MUST HAVE | React.js, Recharts, Axios | Kuruba Ashok | 2- In Progress
S7 | S7 | US-001 | Frontend–Backend Integration – Connect React frontend to FastAPI via Axios; configure CORS middleware | MUST HAVE | React.js, FastAPI, CORS Middleware | Kuruba Ashok | 2- In Progress
S8 | S8 | US-001 | Deployment and CI/CD – Deploy FastAPI backend on Render and React on Vercel; set up GitHub Actions pipeline | MUST HAVE | Render, Vercel, GitHub Actions | Kuruba Ashok | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 16 | 7 | 10 | 4 | 8 | 5 | 6 | 4 | 6 | 3 | 5 | 8 | 6 | 14
SPRINT 1 BACKLOG
US-001 | T-01 | Project Kickoff – Initialize GitHub repo, define folder structure and virtual environment | 2026-02-02 | 2026-02-04 | Leena Gavande | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-02 | Workflow Creation – Design system architecture and data flow for ML pipeline | 2026-02-05 | 2026-02-07 | Leena Gavande | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-03 | Agile Document Preparation – Set up Product Backlog, Sprint Backlog and Retrospection sheets | 2026-02-09 | 2026-02-09 | Leena Gavande | Others | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-04 | Financial API Research – Evaluate Yahoo Finance and Stooq APIs; test NSE ticker download | 2026-02-10 | 2026-02-11 | Leena Gavande | Others | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-05 | API Data Fetching – Write Python scripts to pull historical OHLCV data for all 10 NSE stocks | 2026-02-12 | 2026-02-13 | Leena Gavande | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | T-06 | Data Preprocessing – Clean missing values, normalize data, flatten MultiIndex columns | 2026-02-16 | 2026-02-18 | Leena Gavande | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-07 | Feature Engineering – Compute 50+ technical indicators: RSI, MACD, Bollinger Bands, ATR, OBV | 2026-02-19 | 2026-02-21 | Leena Gavande | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0
US-001 | T-08 | Random Forest Model Training – Train and evaluate RF model with RobustScaler and feature selection | 2026-02-23 | 2026-02-25 | Leena Gavande | Build | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
US-001 | T-09 | Stacking Ensemble – Train XGBoost, LightGBM, ET; build Stacking Ensemble; save 10 pkl files | 2026-02-26 | 2026-02-27 | Leena Gavande | Build | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
SPRINT 3 BACKLOG
US-001 | T-10 | FastAPI Project Setup – Create FastAPI project structure with CORS middleware and routing | 2026-03-02 | 2026-03-03 | Gowthama R. | Build | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-11 | Prediction Endpoint – Implement /predict API endpoint that loads pkl and returns BUY/HOLD/SELL signal | 2026-03-04 | 2026-03-06 | Gowthama R. | Coding | 3- Completed | 6 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-12 | ML Pipeline Integration – Integrate pkl loading, scaler, selector into FastAPI prediction endpoint | 2026-03-09 | 2026-03-13 | Leena Gavande, Gowthama R. | Integration Test | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | T-13 | Dashboard UI Design – Create React wireframes and design layout for signal dashboard | 2026-03-16 | 2026-03-18 | K. Ashok | Design | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0
US-001 | T-14 | React Components – Build signal cards, probability bars, price chart and SignalBadge components | 2026-03-19 | 2026-03-23 | K. Ashok | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 0
US-001 | T-15 | Filter Controls – Add stock symbol filter and BUY/HOLD/SELL filter to dashboard | 2026-03-24 | 2026-03-27 | K. Ashok | Coding | 2- In Progress | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
SPRINT 5 BACKLOG
US-001 | T-16 | Frontend–Backend Integration – Connect React to FastAPI via Axios; test all signal endpoints | 2026-03-30 | 2026-03-31 | K. Ashok, Gowthama R. | Integration Test | 2- In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-17 | Backend Deployment – Deploy FastAPI on Render with environment variables and keep-alive logic | 2026-03-30 | 2026-03-31 | Karishma K. | System Test | 2- In Progress | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-18 | Frontend Deployment – Deploy React app on Vercel; configure CORS and environment variables | 2026-04-01 | 2026-04-01 | Karishma K. | System Test | 2- In Progress | 5 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-19 | End-to-End Testing and Documentation – Run full integration tests; write README and deployment guide | 2026-04-02 | 2026-04-02 | Leena Gavande, Gowthama R., K. Ashok, Karishma K. | System Test | 2- In Progress | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear which NSE APIs are reliable — Yahoo Finance returning NoneType errors for .NS tickers | Tested 4 sources; selected curl_cffi + Stooq as primary fallback; documented decision in README
Sprint 1 | Day 4 | Uncertainty on how to design the feature engineering pipeline to avoid data leakage | Team discussion held; decided to use TimeSeriesSplit CV; adaptive ATR-based labels designed
Sprint 2 | Day 6 | API rate limits when fetching 5 years of OHLCV data for all 10 NSE stocks simultaneously | Implemented sequential download with sleep() delay; Stooq used as fallback for rate-limited tickers
Sprint 2 | Day 8 | Missing values and inconsistent date formats in raw OHLCV data from Yahoo Finance | Applied forward-fill and dropna; standardized date index; added assert checks inside _clean()
Sprint 2 | Day 11 | Overfitting observed in initial Random Forest model — CV accuracy 91% but test accuracy 64% | Applied RobustScaler, SelectFromModel feature selection, and TimeSeriesSplit; accuracy stabilised at 80%+
Sprint 3 | Day 14 | Selector and scaler objects in pkl files incompatible with Gowthama's FastAPI sklearn version | Aligned sklearn version across team; regenerated all 10 pkl files; shared pkl schema doc with backend
Sprint 4 | Day 18 | Re-training all 10 models slow — taking 45+ minutes; blocking integration testing | Parallelised training loop; reduced Stacking CV folds from 5 to 3; training time reduced to 20 min
Sprint 5 | Day 23 | HINDUNILVR model test accuracy stuck at 77% after retraining — below 80% target | Tuned LightGBM hyperparameters (num_leaves=31, lr=0.01); accuracy reached 81% on hold-out test

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-13 | Leena Gavande | Documenting data pipeline steps and API integration decisions from day one | Skipping data validation to save time — caused silent NaN bugs in feature columns | Conducting daily stand-ups and using GitHub for version control | Added assert checks inside _clean(); created shared data pipeline doc on GitHub Wiki
2 | Sprint 2 | 2026-02-16 | 2026-02-27 | Leena Gavande | Logging ML model training metrics (accuracy, F1-score) after each experiment run | Pushing untested or undocumented code directly to the main branch | Regular pair-programming and code review sessions with Gowthama | Implemented structured experiment logging using CSV; enforced PR review before merge
3 | Sprint 3 | 2026-03-02 | 2026-03-13 | Leena Gavande | Sharing pkl file schema and predict() API contract with Gowthama before integration | Hardcoding file paths and sklearn version — caused pkl loading failures in FastAPI | Modular code design; separating feature engineering from model training logic | Moved all configs to config dict; aligned sklearn version; regenerated all 10 pkl files
4 | Sprint 4 | 2026-03-16 | 2026-03-27 | Leena Gavande | Setting a weekly accuracy threshold check to catch model regressions early | Re-training all 10 models at once without checking which ones changed | TimeSeriesSplit CV — prevents data leakage and gives realistic accuracy scores | Added per-stock accuracy diff report after each retrain; tagged pkl files with version date
5 | Sprint 5 | 2026-03-30 | 2026-04-02 | Leena Gavande, Gowthama R., K. Ashok, Karishma K | Running end-to-end integration tests before each deployment to catch issues early | Waiting until the final sprint to perform integration and deployment testing | Agile sprint retrospectives, open team communication, and collaborative code reviews | All integration tests passed; platform deployed successfully on Render and Vercel